## Sheet1
Color Coding |  |  | Completed |  |  |  | Fall 2019 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2019-09-10 | 2019-09-17 | 2017-09-24 | 2018-10-01 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17
Project Phase | Activity |  | Team Member | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-10 | 100%
| Prioritize project ideas |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Estimation of cost and schedule |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Development of the business case |  | Andrew Paykin | 2019-09-10 | 2019-09-17 | 100%
| Project environment preparation |  | Poovadol Pradubsri | 2019-09-17 | 2019-09-24 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | Poovadol Pradubsri | 2019-09-17 | 2017-09-24 | 100%
| Determine project features |  | Poovadol Pradubsri, Hao Dong | 2019-09-10 | 2019-09-17 | 100%
| Organize Project Team |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-10 | 100%
| Definition of Software Methodology |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Make Project Plan |  | Poovadol Pradubsri | 2019-09-25 | 2019-10-01 | 100%
| Make RACI |  | Poovadol Pradubsri | 2019-09-25 | 2019-10-01 | 100%
| Make PID document |  | Poovadol Pradubsri | 2019-09-25 | 2019-10-01 | 100%
| Make BRM Diagram |  | Hao Dong | 2019-10-10 | 2019-10-15 | 100%
| Make User roles |  | Hao Dong | 2019-10-10 | 2019-10-15 | 100%
| Make Context Diagram |  | Andrew Paykin | 2019-10-10 | 2019-10-15 | 100%
| Make System interface table |  | Andrew Paykin | 2019-10-10 | 2019-10-15 | 100%
| Make Requirements Types, include tasks in Project Plan |  | Andrew Paykin | 2019-10-10 | 2019-10-15 | 100%
| Finish Updated project plan |  | Poovadol Pradubsri | 2019-10-10 | 2019-10-15 | 100%
| Make Business Requirement |  | Hao Dong | 2019-10-16 | 2019-10-22 | 40%
| Make Functional Decomposition |  | Andrew Paykin | 2019-10-16 | 2019-10-22 | 100%
| Make Fishbone Diagrams |  | Andrew Paykin | 2019-10-16 | 2019-10-22 | 100%
| Make RCT (includes supplementary reqs) |  | Andrew Paykin | 2019-10-16 | 2019-10-22 | 50%
| Finish Updated Project Plan |  | Poovadol Pradubsri | 2019-10-16 | 2019-10-22 | 90%
| Select in the RCT a few features to implement |  | Poovadol Pradubsri, Hao Dong | 2019-10-23 | 2019-10-29 | 0%
| Make UML analysis diagrams (use case, activity diagrams) |  | Andrew Paykin | 2019-10-23 | 2019-10-29 | 0%
| Make Data-flow Diagram (logical) |  | Andrew Paykin | 2019-10-23 | 2019-10-29 | 0%
| Make Functional Requirements (user stories) |  | Andrew Paykin | 2019-10-23 | 2019-10-29 | 0%
| Finish Updated Project Plan |  | Poovadol Pradubsri | 2019-10-23 | 2019-10-29 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Register function design |  | Andy Mech, Ryan, Jaepil | 2019-10-15 | 2018-10-22 | 0%
| Menu function Design |  | Jaepil Lee | 2019-10-01 | 2019-10-15 | 0%
| Reservation function Design |  | Andy Mech, Ryan, Jaepil | 2019-11-12 | 2019-11-19 | 0%
| Payment function design |  | Andy Mech, Ryan, Jaepil | 2019-11-19 | 2019-11-26 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | User Portal for regsiter account and look up menu | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-12 | 2019-11-19 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-12 | 2019-11-19 | 0%
| Admin Portal for edit and update menu | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-12 | 2019-11-26 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-12 | 2019-11-26 | 0%
| Reservation and Order interface | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
| Payment interface | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  | ALL | 2019-11-26 | 2019-12-17 | 0%
| Evaluate Features to be Tested |  | ALL | 2019-11-26 | 2019-12-17 | 0%
| User Portal | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Admin Portal | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Make Order | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Process Order | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-12-03 | 2019-12-17 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
Implementation | Deploy Application For Presentation Demo |  | ALL | 2019-12-10 | 2019-12-17 | 0%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | ALL | 2019-12-10 | 2019-12-17