## Sheet1
Color Coding |  |  | Completed |  |  |  | Fall 2019 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2019-09-10 | 2019-09-17 | 2017-09-24 | 2018-10-01 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17
Project Phase | Activity |  | Team Member | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-10 | 100%
| Prioritize project ideas |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Estimation of cost and schedule |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Development of the business case |  | Andrew Paykin | 2019-09-10 | 2019-09-17 | 100%
| Project environment preparation |  | Poovadol Pradubsri | 2019-09-17 | 2019-09-24 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | Poovadol Pradubsri | 2019-09-17 | 2017-09-24 | 100%
| Determine project features |  | Poovadol Pradubsri, Hao Dong | 2019-09-10 | 2019-09-17 | 100%
| Organize Project Team |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-10 | 100%
| Definition of Software Methodology |  | Poovadol Pradubsri | 2019-09-10 | 2019-09-17 | 100%
| Gathering of Business Requirements |  | Andrew Paykin, Hao Dong | 2019-09-17 | 2017-09-24 | 100%
| Business Requirements Analysis |  | Andrew Paykin, Hao Dong | 2019-09-17 | 2017-09-24 | 100%
| System Requirements definition |  | Andrew Paykin, Hao Dong | 2017-09-24 | 2018-10-15
| BRM Diagram |  | Hao Dong | 2019-10-01 | 2019-10-15
| Context Diagram |  | Andrew Paykin | 2019-10-01 | 2019-10-15
| Business Requirements Diagram |  | Hao Dong | 2019-10-01 | 2019-10-15
| Requirements prioritization |  | Poovadol Pradubsri | 2019-10-01 | 2018-10-15
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design |  | Andy Mech, Ryan, Jaepil | 2019-10-15 | 2018-10-22 | 0%
| Database Design |  | Jaepil Lee | 2019-10-01 | 2019-10-15 | 0%
| System Interface Design |  | Andy Mech, Ryan, Jaepil | 2019-11-12 | 2019-11-19 | 0%
| User interface design |  | Andy Mech, Ryan, Jaepil | 2019-11-19 | 2019-11-26 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | User Portal | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-12 | 2019-11-19 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-12 | 2019-11-19 | 0%
| Admin Portal | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-12 | 2019-11-26 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-12 | 2019-11-26 | 0%
| Make Order | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
| Process Order | GUI & Functionality Design | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
|  | Coding | Andy Mech, Ryan | 2019-11-26 | 2019-12-03 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  | ALL | 2019-11-26 | 2019-12-17 | 0%
| Evaluate Features to be Tested |  | ALL | 2019-11-26 | 2019-12-17 | 0%
| User Portal | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Admin Portal | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Make Order | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
| Process Order | Design Test Cases | Janielle Vazquez | 2019-11-26 | 2019-12-10 | 0%
|  | Execute Test Cases | Janielle Vazquez | 2019-12-03 | 2019-12-17 | 0%
|  | Anaylze Test Results | ALL | 2019-12-10 | 2019-12-17 | 0%
Implementation | Deploy Application For Presentation Demo |  | ALL | 2019-12-10 | 2019-12-17 | 0%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | ALL | 2019-12-10 | 2019-12-17